## SCORECARD
S/N | State | SLA | Disbursement - million | Start Up Staff | Peer Learning | Orientation and AWPB | AWPB | LGA | COM | Full Staff – Others | LPIU Staffing | WF Staffing | WAG FORMATION | Comment or remark
Approved
1 | Ekiti | Yes | 3 | Yes | Yes | Yes | Yes | Daura Funtua Katsina | Yes | Proj Sec |  | Efon Cleared – 96 BUT ONLY 67 showed up for training, Cleared Aiyekirie and Moba | 105 | Susan and Busayo additional Moba
2 | Katsina | Yes | 3 | SPC | Yes | Yes | Yes | Daura Funtua Katsina | Yes | Yes | Outstanding LFS and WAGSO -1 Funtua | Daura 76 Cleared | No
3 | Ogun | Yes | 3 | Yes | N/A | Yes | No | Ado Ota Ifo Sagamu Ijebu Ode | Yes | BCC Anchor | Yes | Yes | 624
4 | Kebbi | Yes | 3 | PO | N/A | Yes | Yes | Zuru Birinin Kebbi Dandi | Yes | BCC Anchor | Outstanding Dandi | No | No
5 | Taraba | Yes | 3 | Yes | N/A | Yes | Yes | Wukari Karim Lamido Sardauna | Yes | Yes | Yes | Zuru - 120 | 467
6 | Jigawa | Yes | 3 | Yes | Yes | Yes | Yes | Dutse, Kazaure, Malamadori | Yes | Yes | Yes | Dutse - 96 | No | Susan , Tope, Sam, Frank, Ishowo , Yvonne - 2 outstanding LGAs
7 | Nasarawa | Yes | 3 | Yes | Yes | Yes | Yes | Awe, Nasarawa and Wamba | No | M &E Anchor and CIB Anchor | No | No | No | To redo LPIU
8 | Delta | Yes | 3 | SPC AND PO | Yes | Yes | Yes | Ika North East, Ethiope East, Warri North | No | Yes | Yes | No | No | Uche and Sam reviewing
9 | Kogi | Yes | 3 | Yes | Yes | Yes | Yes | Dekina, Okene, Yagba East | No | Yes |  | No | No
10 | Borno | Yes | 3 | Yes | Yes | Yes | Yes | Damboa, Marte, Dikwa | Yes | Social GBV team | Outstanding LFS Marte | No | No | Finance Officer and GBV Advisor
11 | Bayelsa | Yes | 3 | Yes- incomplete (Procurement and HOP) | Yes | Yes | Y | Sagbama, Ogbia, Kolokuma Opkpokuma | No | OutB Team and M and E team, | Not well done |  | No
12 | Ebonyi | Yes | 3 | Yes | Yes | Yes | Y | Izzi, Ikwo, Afikpo | N | Outstanding MIS , E and S team,CIB, LLH , BCC Anchor , IT support staff | Izzi – Yes and Akpi – LFS and 2 wagsos outstanding |  | No
No
13 | Yobe | Yes | 3 | PA | Yes | Yes | Y | Fune, Gujba, Nguru | Yes | Yes | Yes | No | No | State yet to provide PA and FO
14 | Adamawa | Yes | 3 | PO | Yes | Yes | Yes | Numan, Madgali, Fufore | Yes | Outstanding CIB Advisor and E and S Officer | No |  | No | Charity and Tope, Social - Lawyer and schooled in francophone
15 | Zamfara | Yes | 3 | Yes | Yes | N | N | Kaura Namoda, Gusau, Maradun | N | No | No |  | No
16 | Kwara | Yes | 3 | Yes | Yes | Yes | Yes | Ifelodun, Moro, Asa | N | Outstanding LLH team, Env, Social Advisor CIB team, BCC Advisor , Proj Sec | No |  | No
17 | Gombe | Yes | 3 | Yes (Pending HOP review) | Yes | Yes | N | Yamaltu Deba, Balanga, Funakaye | N | N | Outstanding LFS Balanga , LPIU Funakaye and Yelteda |  | No
18 | Anambra | Yes |  | Yes | Yes | Yes | N | Njikoka, Ogbaru, Aguata | N | N |  |  | No
19 | Ondo | Yes | 3 | Yes (Pending procurement officer) | Yes | Yes | N | Akoko North West, Akure North, Ilaje |  |  |  |  | No
| Abia | Yes | 0 | No | N/A | No | N |  | N | N |  |  | No
No
20 | Akwa Ibom | Yes | 0 | No | N/A | No | N |  | N | N |  |  | No
21 | Niger | Yes | 0 | No | N/A |  | N |  | N | N |  |  | No
22 | Bauchi | Yes | 0 | No |  | No | N |  | N | N |  |  | No
23 | Cross River | Yes | 0 | No |  |  | N |  | N | N |  |  | No
24 | Sokoto | Yes | 0 | Outstanding PO |  |  | N |  | N | N |  |  | No
26 | Osun | Yes | 0 | No |  |  | N |  | N | N |  |  | No
|  |  |  | No | [8 empty] | No
27 | Plateau | Yes | 0 | SPC , HOP and PO |  |  | N |  | N | N |  |  | No
28 | Benue | Yes | 0 | No |  |  | N |  | N | N |  |  | No
29 | Enugu | Yes | 0 | SPC, PIA and PA | N/A |  | N | Nsukka, Nkanu, Udi | N | N |  |  | No
30 | Edo | Yes | 0 | No | [8 empty] | No
31 | Lagos | No | 0 | No | [8 empty] | No
32 | Kano | No | 0 | No |  |  | N |  | N | N |  |  | No
33 | Kaduna | No | 0 | No |  |  | N |  | N | N |  |  | No
34 | FCT | No | 0 | No |  |  | N |  | N | N |  |  | No
35 | Rivers | No | 0 | No |  |  | N |  | N | N |  |  | No
36 | Oyo | No | 0 | No |  |  | N |  | N | N |  |  | No
37 | Federal | Yes | 3 | Yes | [5 empty] | N |  |  | No | a. TOR for SRA and sample SRA and SRM from other projects b. Sample GM for project workers and community workers that can guide the NFWP. | N | N
|  |  | 57 | No

## M and E training
States | M&E Anchor | M&E Advisor | MIS Specialist | Others | Total | TOTAL STATES TRAINED | 10
Abia | Did not attend | Did not attend | Did not attend |  | 0 | STATES NOT TRAINED | 27
Adamawa | Did not attend | Kenan Allahdon | Did not attend |  | 0 | TOTAL PERSONS TRAINED | 28
Akwa Ibom | Did not attend | Did not attend | Did not attend |  | 0
Anambra | Did not attend | Did not attend | Did not attend |  | 0
Bauchi | Did not attend | Did not attend | Did not attend |  | 0
Bayelsa | Did not attend | Did not attend | OGBE AYAWEI |  | 0
Benue | Did not attend | Did not attend | Did not attend |  | 0
Borno | Did not attend | Did not attend | Did not attend |  | 0
Cross River | Did not attend | Did not attend | Did not attend |  | 0
Delta | Avwomakpa Revival | Oderhohwo Faith Oberhiri | Bobi Onoriode Zion |  | 3
Ebonyi | Did not attend | Did not attend | Did not attend |  | 0
Edo | Did not attend | Did not attend | Did not attend |  | 0
Ekiti | Akindoyeni Temitope Lizzy | Ayeni Oluwasola | Adermnole Stephen |  | 3
Enugu | Did not attend | Did not attend | Did not attend |  | 0
Gombe | Did not attend | Did not attend | Did not attend |  | 0
Imo | Did not attend | Did not attend | Did not attend |  | 0
Jigawa | Did not attend | Ibrahim Adamu | Muhammad Huwal Sani |  | 2
Kaduna | Did not attend | Did not attend | Did not attend |  | 0
Kano | Did not attend | Did not attend | Did not attend |  | 0
Katsina | Mubaram Jibril | Auwal Abubakar Aminu | Ibrahim Hamisu |  | 3
Kebbi | Aminu Abdullah Yari | Suleiman Ahmad Fingilla | Mustapha Malami IDINA |  | 3
Kogi | Kashim Idakwo | Did not attend | Joseph Sunday Are |  | 2
Kwara | Did not attend | Did not attend | Did not attend |  | 0
Lagos | Did not attend | Did not attend | Did not attend |  | 0
Nasarawa | Did not attend | Did not attend | Did not attend |  | 0
Niger | Gimba Adamu Usman | Ahmad Mohammed | Abubakar Saliadsi Alhassam |  | 4
Ogun | Adekoya Adeoluwa Adekunle | Ibrahim Yusuf | Did not attend |  | 2
Ondo | Did not attend | Did not attend | Did not attend |  | 0
Osun | Did not attend | Did not attend | Did not attend |  | 0
Oyo | Did not attend | Did not attend | Did not attend |  | 0
Plateau | Did not attend | Did not attend | Did not attend |  | 0
Rivers | Did not attend | Did not attend | Did not attend |  | 0
Sokoto | Did not attend | Did not attend | Did not attend |  | 0
Taraba | Kalavo Thomas Kwalla | Rika J.J. Danbeki | Gambo Emmanuel Asogume |  | 3
Yobe | Did not attend | Did not attend | Did not attend |  | 0
Zamfara | Did not attend | Did not attend | Did not attend |  | 0
Federal Capital Territory (FCT): Abuja | Did not attend | Did not attend | Adeniji Ismael Adelami |  | 3
28

## November
November 2025
SUNDAY | MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY | SATURDAY | Peer Learning - CRS , Enugu , Bauchi, Oyo , Lagos and ,Sokoto
2025-10-26 | 2025-10-27 | 2025-10-28 | 2025-10-29 | 2025-10-30 | 2025-10-31 | 2025-11-01 | Batch 1 Orientation - Abia, CRS , Enugu , Lagos and ,Sokoto , HC and PO Anambra , PO Kwara and any state that may not have attended orientation | Batch 2 Orientation - Abia , Akwa Ibom, Niger, Bauchi and Oyo
[7 empty] | Batch 1 COM - Borno, Yobe , Kogi and Adamawa TT - Dr Funke and Uchenna FPCU SPCU - Ibrahim , Rita , Ande , Taiwo | Batch 2 - COM Delta, Niger, Nasarawa, Gombe - Uchenna and Dr Funke SPCU- Ajibade , Taiwo , Katsina Lady -, Rita
2025-11-02 | 2025-11-03 | 2025-11-04 | 2025-11-05 | 2025-11-06 | 2025-11-07 | 2025-11-08
Yola - Charity Sokoto - TTL , IERD Lagos / Ibadan - Yetunde Gombe - Funke and Eyong | Yetunde - Lagos Yobe - Charity and ?? Zamfara - FPCU, Koko and Suleiman | Yetunde - Lagos Yobe - Charity and ?? Zamfara - FPCU, Koko and Suleiman | Yetunde - Lagos Yobe - Charity and ?? Zamfara - FPCU, Koko and Suleiman | Yetunde - Lagos Yobe - Charity and ?? Zamfara - FPCU, Koko and Suleiman | Yetunde - Lagos Yobe - Charity and ?? Zamfara - FPCU, Koko and Suleiman | Yetunde - Lagos Yobe - Charity and ?? Zamfara - FPCU, Koko and Suleiman | Ebonyi, Cross River, Abia and Enugu in the coming days.
2025-11-09 | 2025-11-10 | 2025-11-11 | 2025-11-12 | 2025-11-13 | 2025-11-14 | 2025-11-15
| Yobe - Charity and ?? Orientation STA Zamfara - FPCU, Koko and Suleiman | Yobe - Charity and ?? Orientation STA Zamfara - FPCU, Koko and Suleiman | Yobe - Charity Zamfara - FPCU, Koko and Suleiman | Yobe - Charity Zamfara - FPCU, Koko and Suleiman CRS - Michael and Eyong Abia - Uchenna | Yobe - Charity Zamfara - FPCU, Koko and Suleiman CRS - Michael and Eyong Abia - Uchenna | COM SECRETARIAT MEETING Zamfara - FPCU, Koko and Suleiman CRS - Michael and Eyong Abia - Uchenna
2025-11-16 | 2025-11-17 | 2025-11-18 | 2025-11-19 | 2025-11-20 | 2025-11-21 | 2025-11-22
|  |  | ORIENTATION COM BATCH 1 Michael - Ekiti | ORIENTATION COM BATCH 1 Michael - Ekiti Nasarawa - Ibrahim | ORIENTATION COM BATCH 1 Michael - Ekiti Nasarawa - Ibrahim | ORIENTATION Michael - Ekiti Nasarawa - Ibrahim
2025-11-23 | 2025-11-24 | 2025-11-25 | 2025-11-26 | 2025-11-27 | 2025-11-28 | 2025-11-29
| ORIENTATION COM BATCH 1 | COM - BATCH 1 COM - BATCH 2 starts | COM - BATCH 1 and 2 | COM - BATCH1 and 2 | COM - BATCH 2 COM - BATCH 3 starts
2025-11-30 | 2025-12-01 | Notes

## December
December 2025
SUNDAY | MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY | SATURDAY
2025-11-30 | 2025-12-01 | 2025-12-02 | 2025-12-03 | 2025-12-04 | 2025-12-05 | 2025-12-06
| COM - BATCH 2 and 3 | COM - BATCH 2 and 3 | COM - BATCH 2 and 3 | COM - BATCH 3 | COM - BATCH 3 |  | Batch 3 - COM Kwara, Ondo ,Bayelsa Abia and Akwa Ibom Ajibade , Taiwo , Katsina Lady -, Rita
2025-12-07 | 2025-12-08 | 2025-12-09 | 2025-12-10 | 2025-12-11 | 2025-12-12 | 2025-12-13
| COM - BATCH 3 Charity | Mission Abuja Charity Sokoto | MEETING WITH HCOWA AND SPCS IN ABUJA Charity Sokoto | FM/PROC Charity Sokoto | FM/PROC Charity Sokoto
2025-12-14 | 2025-12-15 | 2025-12-16 | 2025-12-17 | 2025-12-18 | 2025-12-19 | 2025-12-20
| MICHAEL - SOKOTO YETUNDE - OGUN | MICHAEL - SOKOTO YETUNDE - OGUN | MICHAEL - SOKOTO YETUNDE - OGUN MISSION DEBRIEF - CMU | MICHAEL - SOKOTO YETUNDE - OGUN MISSION DEBRIEF -IERD | MICHAEL - SOKOTO YETUNDE - OGUN AIDE MEMOIRE READY | DEBRIEF WITH TEAM
2025-12-21 | 2025-12-22 | 2025-12-23 | 2025-12-24 | 2025-12-25 | 2025-12-26 | 2025-12-27
2025-12-28 | 2025-12-29 | 2025-12-30 | 2025-12-31 | 2026-01-01 | 2026-01-02 | 2026-01-03
2026-01-04 | 2026-01-05 | Notes