## Sheet1
S/No | x | SLA | Disbursement | Start Up Staffing | Full Staff | Peer Learning | Orientation & AWPB | AWPB Approved | LGA | LPIU Recruitment | COM | WF Recruitment | WAG Formation | Comment
1 | FC¦Abuja | No | 0 | No | No | No | No | No | No | No | No | No | 0
2 | AB¦Abia | Yes | 0 | HOP and PO | M and E Advisor LLH Advisor | N/A | Yes | No | Isialangwa South Arochukwu Ugwunagbo | No | No | No | 0
3 | AD¦Adamawa | Yes | 3 | PIA | Gender , GBV and Social Safeguards Advisor & Anchor Enviromental Officer | Yes | Yes | Yes | Numan Madgali Fufore | Yes | Yes | No | 0 | WAG Formation and Support in January
4 | AK¦Akwa Ibom | Yes | 0 | No | No | N/A | No | No | No | No | No | No | 0
5 | AN¦Anambra | Yes | 3 | PIA | No | Yes | Yes | No | Njikoka Ogbaru Aguata | No | No | No | 0 | Ongoing Just In time mission
6 | BA¦Bauchi | Yes | 0 | HOP | No | Yes | Yes | No | No | No | No | No | 0 | Just In time mission in January
7 | BY¦Bayelsa | Yes | 3 | HOP and PO | FO M and E Advisor and Anchor CIB Advisor | Yes | Yes | Yes | Sagbama Ogbia Kolokuma/ Opkpokuma | No | No | No | 0 | Just In time mission in January
8 | BE¦Benue | Yes | 0 | No | No | No | No | No | No | No | No | No | 0 | Just In time mission in January
9 | BO¦Borno | Yes | 3 | Yes | Gender , GBV and Social Safeguards Advisor & Anchor Enviromental Officer | Yes | Yes | Yes | Damboa Marte Dikwa | Yes | Yes | No | 0
10 | CR¦Cross River | Yes | 0 | No | No | No | No | No | Bekwara Odukpani Obubra | No | No | No | 0 | Review of Start up and outstanding staff
11 | DE¦Delta | Yes | 3 | SPC and PO | Yes | Yes | Yes | Yes | Ika North East Ethiope East Warri North | Yes | Yes | No | 0 | WAG Formation and Support in January
12 | EB¦Ebonyi | Yes | 3 | Yes | Gender , GBV and Social Safeguards Advisor & Anchor Enviromental Officer CIB Team LLH Team ICT BCC Anchor | Yes | Yes | Yes | Izzi Ikwo Afikpo | Akpi – LFS and 2 wagsos Ikwo | No | No | 0 | Just In time mission in January
13 | ED¦Edo | Yes | 0 | No | No | No | No | No | No | No | No | No | 0 | Just In time mission in January
14 | EK¦Ekiti | Yes | 3 | Yes | Proj Sec | Yes | Yes | Yes | Moba Aiyekire Efon Alaye | Yes | Yes | Yes | 135 | Slow progress despite been the first mover state
15 | EN¦Enugu | Yes | 3 | PIA and PO | No | No | No | No | Nsukka Nkanu East Udi | No | No | No | 0 | Review of Start up and outstanding staff once shared
16 | GO¦Gombe | Yes | 3 | PO | Proj Sec | Yes | Yes | Yes | Yamaltu Deba Balanga Funakaye | 2 wagsos in Yamaltu Deba | Yes | No | 0
17 | IM¦Imo | No | 0 | No | No | No | No | No | No | No | No | No | 0
18 | JI¦Jigawa | Yes | 3 | Yes | Yes | Yes | Yes | Yes | Dutse Kazaure Malamadori | Yes | Yes | Yes | 260
19 | KD¦Kaduna | No | 0 | No | No | No | No | No | No | No | No | No | 0
20 | KN¦Kano | No | 0 | No | No | No | No | No | No | No | No | No | 0
21 | KT¦Katsina | Yes | 3 | Admin Officer | Yes | Yes | Yes | Yes | Daura Funtua Katsina | Outstanding LFS and WAGSO -1 Funtua | Yes | Outstanding Funtua and Katsina | 3 | Slow progress despite been the first mover state.
22 | KE¦Kebbi | Yes | 3 | PO | Yes | N/A | Yes | Yes | Zuru Birinin Kebbi Dandi | Outstanding Dandi | Yes | Outstanding Birrin Kebbi and Dandi | 0 | Fast Track Community Level Activities and engagement of the PO
23 | KO¦Kogi | Yes | 3 | Yes | Yes | Yes | Yes | Yes | Dekina Okene Yagba East | Yes | Yes | No | 0
24 | KW¦Kwara | Yes | 3 | Yes | Yes | Yes | Yes | Yes | Ifelodun Ilorin West Edu | Outstanding Ifelodun and Edu | Yes | No | 0 | Review of LPIU outstanding staff once shared
25 | LA¦Lagos | Yes | 0 | No | No | No | No | No | No | No | No | No
26 | NA¦Nassarawa | Yes | 3 | Yes | Yes | Yes | Yes | Yes | Awe Nasarawa Wamba | Outstanding 2 WAGSO Wamba | Yes | No | 0
27 | NI¦Niger | Yes | 0 | PO | No | N/A | No | No | No | No | No | No | 0
28 | OG¦Ogun | Yes | 3 | Yes | BCC Anchor | Yes | Yes | Yes | Ado Ota Ifo Sagamu Ijebu Ode | Yes | Yes | Yes | 1613
29 | ON¦Ondo | Yes | 3 | PO | Outstanding LLH team, Env,and Social Advisor and Anchor CIB, BCC Advisor Proj Sec , LLH Team | Yes | Yes | Yes | Akoko North West Akure North Ilaje | No | No | No | 0
30 | OS¦Osun | Yes | 0 | No | No | No | No | No | No | No | No | No | 0
31 | OY¦Oyo | Yes | 0 | No | No | No | No | No | No | No | No | No | 0
32 | PL¦Plateau | Yes | 0 | No | No | No | No | No | No | No | No | No | 0
33 | RI¦Rivers | No | 0 | No | No | No | No | No | No | No | No | No | 0
34 | SO¦Sokoto | Yes | 0 | PO | No | Yes | Yes | No | Sokoto South Gwadabawa Dange Shuni | No | No | No | 0
35 | TA¦Taraba | Yes | 3 | Yes | Yes | N/A | Yes | Yes | Wukari Karim Lamido Sardauna | Yes | Yes | Yes | 949
36 | YO¦Yobe | Yes | 3 | Yes | Yes | Yes | Yes | Yes | Fune Gujba, Nguru | Yes | Yes | No | 0
37 | ZA¦Zamfara | Yes | 3 | Yes | Yes | Yes | Yes | No | Kaura Namoda Gusau Maradun | Yes | Yes | No | 0
38 | Federal | Yes | 3 | Yes | Yes | Yes | Yes | No | N/A | N/A | N/A | N/A | N/A
|  |  | 63 | [9 empty] | 2520